## Sheet1
Project | [G-Reg 5.0.0] Improved Notifications Support
Time period | 28/05/2014 - 18/06/2014
Members | Heshani Gamage
Stakeholders
Redmine | https://redmine.wso2.com/issues/2342
Milestone | Delievrables | Tasks | Planned end date | Status | End Date
Milestone 1 |  | Requirment gathering |  | in progress
|  | Research of common Roles and Notifications |  | in progress
|  | Design the UI |  | not started | 15/08/2014
Milestone 2 | Backend service method for Add Version | Check whether this is possible with existing handler |  | in progress
|  | New method for Add version | 11.09.2014
Milestone 3
Milestone 4